Defining and Evaluating CSCL Projects

Managing Towards Evaluation

- John Nash*, Leo Plugge§, Anneke Eurelings§

* Stanford Learning Laboratory,

Stanford University, Stanford, CA 94305, U.S.A.

§ Maastricht McLuhan Institute Learning Laboratory,

University of Maastricht, 6200 MD Maastricht, The Netherlands.

Abstract

Preparing, managing and evaluating educational technology initiatives, including projects that involve computer support for collaborative learning (CSCL), is a difficult task due to the numerous variables involved. In this paper, we propose a method to implement a “theory of change” approach to CSCL projects. The academic-sounding phrase “theory of change” is basically a way to ask, "What is the project designed to accomplish, and how are its components intended to get it there?" The method helps project teams articulate their own theory of change and specify goals, outcomes and indicators, leading to an evaluation plan for the project that is satisfying to the target group, the implementers, and the funding parties. The method proposed is aimed at all participants involved, but in particular those who have the responsibility to design the educational technology projects. The method also offers assistance in determining evaluation criteria for the project. The paper discusses problems inherent in the articulation, planning and evaluation of CSCL initiatives, and draws out the initial steps necessary to implement a theory of change approach.

Keywords: theory based evaluation; project preparation; project management.

# Introduction

The explosive growth and functionality of Information and Communication Technology (ICT) in general, and the Internet in particular, has spurned discussion how to embrace this revolution for learning. Universities are under increasing pressure to use this technological innovation as a means to control costs, improve quality, and operate more flexible and client-centered. Given the millions of dollars that are spent on ICT, there is an increasing call for accountability. The question is simple: does teaching and learning benefit from these investments? Obtaining the answer, however, is complicated. It means appraising the effect of our intervention (Phipps, 1999). An often-heard complaint is that evaluation methodology is subverted by a myriad of confounding variables brought on by others involved in the project. Why is this happening and how can we avoid this?

We suggest that this problem arises out of four common misconceptions about educational technology projects. These misconceptions cause a “garbage in, garbage out” effect, i.e., the evaluation cannot be better than the parameters built into the project from the start.

In the remainder of this paper, we first discuss these misconceptions and then propose a method to help projects avoiding these evaluation traps.

# Four Prevailing Misconceptions

## Misconception I: The Common Goal

Many projects start out by trying to create one common goal. This neglects the fact that projects have different stakeholders, i.e., those who have some stake in the project: the way the project runs, the end results, the tools used, the effects of the results, etc. The stake of people participating in a project can be very different. One group or persons might wish to enhance learning, while others may just wish to force the department controlling the infrastructure to adopt a different type of technology. Thus, there is probably a different goal for every stakeholder, in particular for stakeholders operating on different domain (organizational) levels. The failure to recognize this results in projects with hidden goals, conflicting goals, creeping goals, and dead goals. Conflicting goals are usually found between two different domain levels, although they can occur within one level between two stakeholders. Conflicting goals usually surface sooner or later, either during the project or during evaluation. Hidden goals, on the other hand, never have to surface. Hidden goals do not even have to be in conflict with other goals. However, they usually surface in the behavior of participants that does not seem to fit with what was agreed. It is often a cause for mistrust, i.e., the assumption that some participants have a hidden agenda. Creeping goals are new goals that enter the project while it is running, i.e., people change their minds or think of something new. It is often a sign that the discussion between the stakeholders was unfinished, or that the requirements analysis was inadequate. Dead goals on the other hand are goals that are no longer pursued. For some reason that goal was no longer thought relevant, or it was simply forgotten. In either case, the project management was not paying attention. It usually surfaces when someone asks, “I thought we were going to…”

Figure 1 Conflicting goals, Dead goals, Creeping goals, and Hidden goals

The point is that by recognizing the existence of different goals at different levels, and with different stakeholders, it becomes clear that it is impossible to unify them into one grand goal. The task of the project management is to create a web of explicit, interconnected, and mutually supporting goals, all sustaining the same common vision.

Personnel charged with evaluating the success of these projects face the challenge to serve many stakeholders, and thus many goals. In general, applied research and evaluation personnel have clients from three major stakeholder groups: the group that is charged with the technical functionality of the project’s product, groups concerned with the ultimate project outcomes, and the students who are supposed to benefit from all this. Having different goals is by itself is not the problem. The problem lies in acknowledging that there are different goals, and how to make them clear and balanced in such a way that they do not become conflicting goals, creeping goals, hidden goals or dead goals.

## Misconception II: The Common Problem

The second problem is closely related to the first misconception: it is the belief that we are addressing a common problem. Analog to the different goals, project participants deal with completely different problems. Some project participants believe they need to solve technical problems; others believe they need to deal with organizational problems. Therefore, it’s likely that project participants work from different perspectives and operate on different levels of change. Even when both the design team and the evaluation team are working to realize a common vision, their individual problems can be very different. These differences depend on the difference in the domains they operate.

For example, a faculty member might endorse the common vision to create a more student-centered environment, but still have as his/her personal goal not to increase the workload or even to reduce their workload. If these issues are not recognized as valid and justified, then they risk behaving as a hidden goal. These types of goals seriously handicap the chance of success of a project.

## Misconception III: The Reductionism’s Simplicity

Given the intricate network of different goals, and the number of interrelated problems, we face yet another difficulty: the inability to reduce the project’s complexity such that it becomes a simple problem. Applying rational and reductionist models of thinking here will only lead to frustration. We believe that the challenge of defining educational technology projects is a so-called “wicked problem.”

Rittel and Webber (Rittel & Webber, 1969) describe wicked problems as follows:

For wicked planning problems, there are no true or false answers. Normally, many parties are equally equipped, interested, and/or entitled to judge the solutions, although none has the power to set formal decision rules to determine correctness. Their judgments are likely to differ widely to accord with their group or personal interests, their special value-sets, and their ideological predilections.

In short, there are four criteria for a problem to be wicked (Conklin & Weil, 1997):

- The problem is an evolving set of interlocking issues and constraints with no definitive statement of the problem.

- There are many stakeholders, i.e., people who care about or have something at stake in how the problem is resolved. Since there is no “right answer”, having stakeholders accept whatever solution emerges is more important than the solution itself.

- The constraints on the solution, such as limited resources and political ramifications, change over time.

- Since there is no definitive Problem, there is no definitive Solution. The problem-solving process ends when you run out of time, money, energy, or some other resource, not when some perfect solution emerges.

In our opinion, CSCL projects are wicked problems. The important stakeholders bring different aspects of wickedness to the solution space for a given problem. In general, all of the groups tend to share three basic traits: they all worry about idiosyncratic issues; they all have opinions about the solution; and they fear not being heard in the discussion leading to the solution. In solo development efforts these issues do not bear so significantly on the problem. Complex development efforts, however, increase the burden several fold. As such, complex initiatives begin to defy simplification and abstraction, and cannot be solved in a linear way. However, that is usually the way we approach educational technology projects: we treat them as tame problems. (Conklin and Weil, 1997) Tame problems lend themselves for traditional, linear, problem-solving methods: define the main goal; formulate the main problem, and think of the best solution. This is the method we are familiar with and therefore approach wicked problems as if they were tame problems. When all you have is a hammer, everything looks like a nail.

## Misconception IV: Usefulness of Traditional Research Paradigms

CSCL initiatives can exhibit broad variations in strategies and activities being pursued. In most cases, the efforts represent complex, multifaceted interventions. There is a growing sentiment that complex multifaceted interventions do not lend themselves to traditional evaluation methods involving randomized control groups or comparison groups to establish counterfactuals. Designing cross-site or even cross-project evaluation frameworks with rigorously specified and consistent outcome measures is very difficult (Hebert & Anderson, 1998) (Hollister & Hill, 1998).

Lisbeth Schorr (Schorr, 1995) proffered the following thoughts about research and evaluation of complex initiatives (Kubisch et al. 1998).

Because of the narrow range of interventions that can be assessed with current evaluation techniques, and the narrow range of information about impacts that current evaluation techniques are able to capture, prevailing approaches to evaluation have not provided the knowledge needed to make good judgments about a range of social programs that may hold the most promise. But current evaluation techniques have managed to systematically bias program design and policy development away from what is likely to be most effective.

By adapting Schorr’s thinking (Schorr, 1995), one begins to see that in order to be rigorously evaluated with traditional methods, CSCL initiatives must be standardized—across sites, students, faculty, and over time. They must be sufficiently constrained such that their activities and effects can be discerned in isolation from other attempts to intervene. Furthermore they must be sufficiently susceptible to outside direction so that features such as to how participants are recruited and selected can be controlled. However, these are conditions that are incompatible with what we know contributes to CSCL project effectiveness:

- Effective projects are adapted to particular sites and individuals;

- they change over time, with continuing mid-course corrections to raise the odds of success;

- they are comprehensive and multi-faceted, f.e., learning and organizational dependency;

- they count on being able to make operational decisions locally.

The complexity does not end here. The fact that CSCL projects involve ICT brings its own set of difficulties (Means, 2000):

- Technology is only one piece of a complex intervention.

- Interventions involving technology require an infrastructure for their implementation.

- Technology-supported interventions are often ill specified and subject to change over time.

- Available measures do not capture all of the hypothesized enhancements.

- Student, faculty, and institution variables are likely to moderate the effects.

- It is difficult to attribute measured effects to technology use.

Keeping in mind the notion attributed to George Box (Box et al., 1978) that “All models are wrong, some are useful,” we turn to the second part of the paper, providing the reader with a model to address the common misconceptions found in the design, deployment and evaluation of CSCL initiatives.

# First Steps in a Theory-Based Evaluation Approach

The first part of this paper introduced some of the misconceptions adopted by project managers and researchers in CSCL-like projects. These misconceptions included the common goal, the common problem, reductionistic simplicity, and traditional research paradigms. In the remainder of the paper we outline an approach rooted in notions of theory-based evaluation, theory of change, and program logic that is designed to help avoiding these misconceptions. Theory-based evaluation looks at the linkages between a program's input and its outcomes via intermediate variables. Weiss (Weiss, 1998) notes four purposes for theory-based evaluation:

- It concentrates evaluation attention and resources on key aspects of the project.

- It facilitates aggregation of results into a broader context of theoretical program knowledge.

- It asks project practitioners to make their assumptions explicit and to reach consensus.

- Evaluations that address the theoretical assumptions embedded in programs may have more influence on both policy and popular opinion.

Cornell and Kubisch (Connel & Kubisch, 1998) identify three more reasons why the design and evaluation of a complex initiative should begin with the articulation of its theory of change:

- It can sharpen the planning and implementation of an initiative.

- It facilitates the measurement and data collection elements of the evaluation process.

- It reduces, but does not eliminate, problems associated with causal attribution of impact.

Among the literature advocating a theory of change approach, few make operational suggestions for complex projects (Milligan et al., 1998). Many references to its implementation are in the context of specific project descriptions, leaving the reader to tease out relevant strategies for their own use. In reviewing the literature on theory-based evaluation, theory of change, program logic, as well as functional requirements specifications practice, we present here the first five steps in implementing a theory of change approach to complex ICT projects. The steps are as follows:

- Identify stakeholders;

- Determine the outcomes of interest for the project;

- Construct a program logic map of the project’s theory of change;

- Describe the functional requirements for the elements of the map;

- Revisit the map over time, fine tuning project direction and evaluation.

## Identifying Stakeholders

Including the right stakeholders in the program theory development process is a crucial aspect of this approach. The Kellogg Foundation Evaluation Handbook notes that

Although this step may be time-consuming and fraught with the potential for conflict, it is one well worth the time and effort. Involving many stakeholders will help ensure that the evaluation process goes more smoothly: more people are invested and willing to work hard to get the necessary information; project staff concerns about evaluation are reduced; the information gathered is more reliable and comes from different perspectives, thus forcing the team to think through the meaning of contradictory information; and the recommendations are likely to be accepted by a broader constituency and implemented more fully and with less resistance. (Kellogg Foundation, 1998)

Intimate knowledge of the initiative’s stakeholder groups shapes the selection of who should participate in the articulation of the initiative’s theory of change. The term “Stakeholders” in our approach includes Clients, Customers, Users, and Other Stakeholders. The client is the person or group that is paying for the development, design and deployment of the project. They can be considered the owner of the delivered system. If you are the evaluator or project leader, you should be able to name the client or clients. It is permissible to have several names, but more than three negates the point. For purposes of definition in this approach, the client has the final acceptance of the “system”, (end product, project outcome, etc.) and thus must be satisfied with the “system” as delivered. Where the “system” is being developed for in-house consumption, the same person may fill the roles of the client and the customer. If you cannot find a name for your client, then perhaps you should not be executing the project.

The customer is the person/s who will “buy” the project results or educational product (the CSCL initiative) from the client. In the case of in-house development the same person often plays the roles of the client and the customer. In the case of a product that is being developed for an international market, there might be a different customer (or customer profile) in each country.

Next, list of the potential users who will experience the product or tool or innovation in the project. This is most likely to be the name of a user group like: “college students,” “design engineers,” “project managers.” Operationally defined, “users” are human beings who interface with the product, tool or innovation in some way.

Attach to each category of users a priority rating. This gives the importance and precedence of the user. The Volere (Robertson & Robertson, 2000) template suggests prioritizing the users into:

- Key users. These are critical to the continued success of the product. Give greater importance to requirements generated by this category of user.

- Secondary users. They will use the product, but their opinion of it has no effect on its long-term success. Where there is a conflict between secondary users' requirements and those of key users the key users take precedence.

- Unimportant users. This category of user is given the lowest priority. It includes infrequent, unauthorized and unskilled users, and people who misuse the product.

By assigning a percentage to each type of user one can assess the amount of consideration given to a user. If some users are considered to be more important to the project, or the organization, then this should be stated because it should affect the way project is designed. Some users may be listed as having no impact on the product. This means that the users will make use of the product, but have no vested interest in it. In other words, these users will not complain, nor will they contribute. Any special information from these users will have a lower design priority.

Finally, consider the roles and (if possible) names of people and organizations who are affected by the initiative or whose input is needed in order to develop, design and deploy the project. Failure to recognize stakeholders results in missing requirements in the project.

Examples of stakeholders include: Users (detailed above), Sponsor, Testers, Technology Experts, System Designers, Marketing Experts, Legal Experts, Domain Experts, Usability Experts, and Representatives of external associations.

For each type of stakeholder identify:

- Stakeholder Identification (some combination of role/job title, person name, organization name),

- Stakeholder Knowledge needed by the project.

- Stakeholder Influence on the design.

## Determine the Outcome of Interest for the Project

The activities described in this section and the following section occurs as a meeting of the stakeholders. Generally the creation of a logic model or theory of change illuminates how complex (and overly large or ambitious) projects are when first articulated. Care should be taken to reduce the model to the components that are necessary to achieve the ultimate goals, beginning by determining the outcome of interest.

What are the guidelines for selecting the outcome of interest—the outcome on whose measurement the value or success of the program is to be judged? Lohr argues that the outcome of interest must be “inherently valued.” The idea here being that the policy relevance of the project—the probability of its usefulness—will be enhanced if the outcome of interest is inherently valued.

How does a project team know if they have inherently valued outcomes? Inherently valued outcomes are those in which there is an interest for its own sake rather than for the sake of achieving something further. Outcome Y is said to be inherently valued as follows:

- If Y is attained, the attainment of outcomes to the right is immaterial—one does not particularly care to learn whether they occurred or even what they are.

- If Y is attained, one is willing to assume that the specified outcomes further to the right will also be attained at a satisfactory level. (Lohr, 1995)

Why bother with this? This method enables evaluators, system designers, managers, and clients, via discussion, to select the outcome of interest to their own satisfaction. Furthermore, when the two considerations above are met, support for the project among the necessary interested parties in significantly strengthened.

A strategy for eliciting the desired outcomes of interest in a project is Vanezky’s “History of the Future” exercise (Vanezky, 2000).

To facilitate this process for complex projects, we propose that the project staff write a history of the future. Imagine that your intervention project is completed and that it succeeded in all of its goals. You are to appear tomorrow at a press conference to explain what you have accomplished. Write a press release for distributing at this meeting, explaining in a few paragraphs what it is that you have accomplished, who is benefiting from this, why it’s important (that is, what problem it solves and why this problem needed to be solved), and what it was that you did that led to or caused this success. (p. 7)

Vanezky notes that this exercise forces project participants to clarify exactly what the outcomes of interest are, why they’re important, and how they might be achieved.

## Construct a Program Logic Map of the Project’s Theory of Change

Program logic maps are constructed during a meeting of the stakeholder group. The map graphically links the inputs to the outputs for the project. A sample program logic map, shown in Figure 3, is comprised of three basic component shapes:

Figure 2 Basic shapes for a program logic map

Moving backward from the outcome of interest, a facilitator (likely the initiative’s evaluator) should take the group of stakeholders through a graphic articulation of the initiative’s theory of change. From the program logic map one can derive a succinct summary statement of the project’s logical path. We provide an example here based upon the sample program logic map shown in Figure 3.

A course offered to college students in geographically disparate sites, is theorized to operate as follows: a project-based community curriculum, coupled with curricular support will lead to increased engagement in the local community by students and increased collaboration among students across communities. Internet connectivity and technology support will lead to increased technology skills on the part of the student thus increasing their ability to collaborate. Increased collaboration is theorized to lead to the creation of a learning community and therefore improved student outcomes.

In time the evaluator should be aware of the underlying assumptions and hypotheses about the relationships among elements in the theory of change and state them explicitly. It is useful to number the arrows in the program logic map and have them correspond with narrative descriptions of the assumptions or hypotheses they represent in a companion document.

Figure 3. Sample Project Logic Map for Fictitious Project

In creating a program logic map, Vanezky (Vanezky, 2000) suggests that the following questions be answered:

- What is innovative about the project? What will the project prove, if implemented properly, that will help others understand how CSCL can improve outcomes?

- Is the map complete and are all necessary intermediate goals identified?

- Are the inputs well planned and are they based upon both experience and empirical research?

- Are the outputs identified with the precision needed to design appropriate evaluations of them?

## Describe the Functional Requirements for the Activities in the Map

We discussed above the misconception of the common goal (section 3.1). Initiating a requirements review is a recommended strategy to allow initiative stakeholders to avoid having a false sense of goal alignment. By engaging in an requirements review of the elements of the program logic map, project teams ensure there are no hidden assumptions. Planners must ask themselves, for every element (rectangle, rounded rectangle, and ellipse): “What is the plan for this input or activity?” Be specific in answering this and ask the source-person of the activity or input to provide some rationale for the activity.

| We draw from Volare (Robertson & Robertson, 2000) again here, but modifying it for our own purposes to suit the needs of CSCL projects. Review your list of stakeholders and attach a statement of the participation that you think will be necessary from them to provide the requirements. Describe the contribution that you expect this stakeholder to provide. Is it design-expertise, tool prototyping, usability requirements etc. If possible, assess the minimum amount of time that this user must spend for you to be able to determine the complete requirements. - Name of map element - Is the element an input, intermediate goal, or ultimate goal? - What are the immediate elements that have some dependency on this element? - Definition of element (a one sentence statement of the intention of the element): - Rationale (a justification for the element) - Source (who raised this element?) - Is this element a piece of software? - Is your organization building it? - Data or indicators that will tell you the element has been reached or completed: | - Who do you need help from to get these data and what is the likely time commitment they will need to provide you with? - How long it will take you to get all the data necessary to indicate that the element is completed or reached? - Degree of stakeholder happiness if this element is successfully implemented. Scale from 1 = uninterested to 5 = extremely pleased. - Measure of stakeholder unhappiness if this element is not part of the final product. Scale from 1 = hardly matters to 5 = extremely displeased. - Pointers to supporting materials about this element |
| --- | --- |

## Continue to Revisit the Map.

Any program logic map expires the moment it’s developed. It is extremely important to continually revisit the map with stakeholders to refine its usefulness as a tool in managing and evaluating the project. Lohr (Lohr, 1995) notes that “what matters is only that someone is interested in the truth or falsity of the theory that a certain program X results in a certain outcome Y and is willing to devote some resources to testing and explaining this.” In this vein, two questions should be asked repeatedly:

Question 1. Why perform or accomplish X (an activity or an outcome)? What is expected to result from X?

The answers to this first question and its sub-question help move the line from the left to the right. Answers to these questions help identify the intermediate outcomes that are needed to lead to the ultimate goals on the right.

Question 2. How can Y be expected to follow from X? What other things, if any, must be done or must occur to make the jump from X to Y believable?

The answers to these questions help to fill gaps in the line and forge stronger links.

# Conclusion

In this paper we have described four common misconceptions or myths about educational technology projects. In light of these misconceptions we offer a management model that enables participants to work together towards better evaluations. This model also offers a handle to develop consensus on best practices methods in educational technology projects. Our model is aimed at all participants involved, but in particular those who have the responsibility to design and evaluate the projects.

To some readers, the approach we have described may sound familiar. Members of the design community may feel as though our approach sounds like how one articulates design rationales. In some ways it does. That is because it draws explicitly on the notion that one must paint a rationale for, and logical picture of, the change they hope to have happen in a CSCL initiative. Design rationales, however, tend to be described within the design community, in language that marks the rationale as the domain of the designer, and thus increasing the probability that the rationale's articulation outside that community will be misconstrued. One finds the same phenomenon in the community that attempts to place a scientific methodological approach to evaluating the outcomes of the design process. The rationales for using a scientific method tend to be articulated in language that marks them as the domain of the social researcher. The theory of change process borrows from both but is not the language of either, thereby shunning any attempts by any disciplinary group to exercise "ownership" of the process. The theory of change process places ultimate goals of the project at the center of the planning and deployment levels, ensuring the project is not only about developing a usable tool, or only about learning outcomes, or only about anything else that could be thrust to the front of a project but only represents a small portion of the project. It ensures that the project is about the collective, intended goals of the project stakeholders.

# References

Phipps, R. (1999) What’s the difference? A Review of Contemporary Research on the effectiveness of Distance Learning in Higher Education. The Institute for Higher Education. Washington.

Rittel, H; Webber, M. (1969). Dilemmas in a general theory of planning. Policy Sciences, 4, Elsevier Science, pp 155-173.

Conklin E.J. & Weil, W. (1997). Wicked Problems: Naming the Pain in Organizations. URL: http://www.gdss.com/wp/wicked.htm.

Hebert, S. & Anderson, A. (1998). Applying a Theory of Change Approach to Two National, Multisite Comprehensive Community Initiatives: Practitioner Reflections. In New Approaches to Evaluating Community Initiatives, Volume 2: Theory, Measurement, and Analysis. Aspen Institute: http://www.aspenroundtable.org/vol2/hebert.htm.

Hollister, R. & Hill, J. (1998). Problems in the Evaluation of Community-Wide Initiatives. In: New Approaches to Evaluating Community Initiatives, Volume 1: Concepts, Methods, and Contexts. Aspen Institute: http://www.aspenroundtable.org/vol1/hollister.htm.

Schorr, Lisbeth B. (1995). New Approaches To Evaluation: Helping Sister Mary Paul, Geoff Canada and Otis Johnson While Convincing Pat Moynihan, Newt Gingrich and the American Public. Speech at the Annie E. Casey Foundation Annual Research/Evaluation Conference September 29, 1995.

Kubisch, A.; Weiss, C.; Schorr, L.; Cornell, J. (1998). Introduction. In: New Approaches to Evaluating Community Initiatives, Volume 1: Concepts, Methods, and Contexts. Aspen Institute:  http://www.aspenroundtable.org/vol1/intro.htm.

Means, B. (2000). Measuring Technology’s Role and Impact. Plenary presentation at the 2nd Annual OERI Technology Evaluation Institute. Ann Arbor, Michigan. Aug. 20-23, 2000.

Box, George E. P., Hunter, J.; Hunter, W. (1978). Statistics for Experimenters: An Introduction to Design, Data Analysis, and Model Building. John Wiley & Sons.

Weiss, C. (1998) Nothing as Practical as Good Theory: Exploring Theory-Based Evaluation for Comprehensive Community Initiatives for Children and Families. In New Approaches to Evaluating Community Initiatives, Volume 1: Concepts, Methods, and Contexts. Aspen Institute: : http://www.aspenroundtable.org/vol1/weiss.htm.

Connel, J. & Kubisch, A. (1998). Applying a Theory of Change Approach to the Evaluation of Comprehensive Community Initiatives: Progress, Prospects, and Problems. In New Approaches to Evaluating Community Initiatives, Volume 2: Theory, Measurement, and Analysis. Aspen Institute:  http://www.aspenroundtable.org/vol2/connell.htm.

Milligan, S.; Coulton, C.; York, P.; Register, R. (1998). Implementing a Theory of Change Evaluation in the Cleveland Community-Building Initiative: A Case Study. In New Approaches to Evaluating Community Initiatives, Volume 2: Theory, Measurement, and Analysis. Aspen Institute: http://www.aspenroundtable.org/vol2/milligan.htm

Kellogg Foundation, W.K. (1998) Evaluation Handbook. Battle Creek, MI: Kellogg Foundation. http://www.wkkf.org/Publications/evalhdbk/

Robertson, J. & Robertson, S. (2000). Volere requirements specification template. Edition 6.1. London: Atlantic Systems Guild.

Lohr, L. (1995). Impact analysis for program evaluation. Thousand Oaks: Sage (p. 19)

Vanezky, R. (2000). Procedures for evaluating the impact of complex educational initiatives. Unpublished manuscript.

ICT stands for Information and Communication Technology and thus stresses the integrated nature of information and communication. ICT better describes the kinds of projects we focus on in this paper. It is also the prevailing term used in Europe; its use is gaining ground in the United States.

Claremont Graduate University, Evaluation Core Courses: http://eval.cgu.edu/lectures/lecturen.htm.

We are grateful for the Volere Requirements Specifications Template for guiding us in this area. We have modified the Volere sections on stakeholders and users for our purposes here. (Robertson & Robertson, 2000).

Here on out we use the term “product” to refer generically to the experience, service, tool, innovation or other outcome that is expected from the CSCL initiative.